## Índice.Index
Português | English
Resumo
Investimentos
Financiamento
Summary
Investments
Financing

## Resumo
Resumo | EGO I | EPA I | EPA II | ETT | EAM | Lote 4 (Leilão 001/2021)
Data do Leilão | 2017-04-24 | 2017-04-24 | 2018-06-28 | 2018-12-20 | 2020-12-17 | 2021-06-30
UF | GO | PA | PA | TO / BA | AM | TO
Extensão (Km) | 136 | 296 | 138.8 | 772 | 408 | SE
Tipo de Circuito | CD | CD | CD | - | CD / CS | -
Potência (MVA) | 1344 | 300 | 1800 | 850 | 2050 | 200
Assinatura do Contrato | 2017-08-11 | 2017-08-11 | 2018-09-21 | 2019-03-25 | - | -
Emissão da Licença de Instalação | 2018-09-13 | 2018-10-02 | 2019-05-06 | 19/10/2020 (2 linhas) | - | -
Prazo Aneel | 2021-08-01 | 2022-02-01 | 2023-03-01 | 2024-03-01 | 2026-03-01 | 2024-09-01
Avanço Físico | 100% | 100% | 73% | 12% | - | -
Antecipação Esperada | 17 meses* | 16 meses* | 12 meses | 14 meses | 12/18 meses | -
Entrada em Operação | 2020-03-01 | 2020-11-01 | - | - | - | -
CAPEX Leilão (R$)** | 295294125.78 | 329790787.72 | 479795926 | 699422704.54 | 882240000 | 74914000
Rap Leilão (R$)** | 58818710 | 65776580 | 78284220 | 116061645.85 | 119712580 | 11008060
Rap Energisa (R$)** | 36702875.04 | 46320000 | 33515000 | 62854451 | 63000000 | 4094777
Deságio | 37.6% | 29.58% | 57.19% | 45.84% | 47.37% | 62.8%
Finalidade | Reforços para atendimento ao estado do Mato Grosso do Sul com aumento da confiabilidade do sistema/qualidade | Reforço para o suprimento à região de Santana do Araguaia e aumento na qualidade e confiabilidade do atendimento aos clientes da região nordeste de Mato Grosso. | Expansão da rede básica para possibilitar o atendimento ao crescimento das cargas da região sudeste do Pará que possui grande atividade minerária e agropecuária | Escoamento do potencial de geração hidráulica e fotovoltaico nos estados da Bahia e do Tocantins, além de suprimento para a região de Dianópolis e Gurupi no estado do Tocantins | Atendimento elétrico à região metropolitana de Manaus e Presidente Figueiredo, no estado do Amazonas. | Suprimento à região de Gurupi
*Antecipação Real
** Números com data base dos respectivos leilões
ÍNDICE

## Investimentos
Cronograma de Desembolso | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
EGO I | 3% | 35% | 49% | 13%
EPA I | 3% | 26% | 46% | 25%
EPA II |  | 1% | 20% | 42% | 33% | 4%
ETT |  |  | 3% | 4% | 59% | 34%
EAM |  |  |  |  | 40.11% | 7.29% | 20.92% | 23.3% | 6.4% | 1.38% | 0.29% | 0.31%
Investimentos já realizados | 2017 | 2018 | 2019 | 2020 | 2021 | Total
EGO I | 6 | 90.5 | 124.1 | 33.8 |  | 254.4
EPA I | 8.7 | 79.7 | 152 | 78 |  | 318.4
EPA II |  | 2.9 | 73.6 | 137.1 | 75.6 | 289.2
ETT |  |  | 15.9 | 33.3 | 32.2 | 81.4
EAM | [5 empty] | 0
| 14.7 | 173.1 | 365.6 | 282.2 | 107.8 | 943.4
ÍNDICE

## Financiamento
Operação Contratada | Debênture de Infra | Fundo Constitucional de Finan.do Norte (Banco da Amazônia) | 4131 | Fundo Constitucional de Finan.do Norte (Banco da Amazônia) | Debênture de Infra | Debênture
Empresa | Energisa Transmissora | EPA I | Energisa Transmissora | EPA II | Energisa Transmissora | Energisa Transmissora
Montante (R$ mm) | 250 | 201.3 | 135 | 250 | 250 | 300
Custo da dívida | 104,6% do CDI | IPCA + 1,88% | CDI + 0,65% | IPCA + 1,68% | 1a série: IPCA + 4,23% 2a série: IPCA + 4,47% | CDI + 1,8%
Prazo | 1ª série: dez/2025 2ª série: dez/2028 3ª série: dez/2025 | 1939-07-01 | 2023-02-01 | 1940-07-01 | 1a série: out/2027 2a série: out/2030 | 2024-03-01
ÍNDICE

## Summary
Summary | EGO I | EPA I | EPA II | ETT | EAM | Block 4 (Auction 001/2021)
Data do Leilão | 2017-04-24 | 2017-04-24 | 2018-06-28 | 2018-12-20 | 2020-12-17 | 2021-06-30
UF | GO | PA | PA | TO / BA | AM | TO
Extensão (Km) | 136 | 296 | 138.8 | 772 | 408 | Sergipe
Tipo de Circuito | DC | DC | DC | - | DC / CS | -
Potência (MVA) | 1344 | 300 | 1800 | 850 | 2050 | 200
Assinatura do Contrato | 2017-08-11 | 2017-08-11 | 2018-09-21 | 2019-03-25 | - | -
Emissão da Licença de Instalação | 2018-09-13 | 2018-10-02 | 2019-05-06 | 10/19/2020 (2 lines) | - | -
Prazo Aneel | 2021-08-01 | 2022-02-01 | 2023-03-01 | 2024-03-01 | 2026-03-01 | 2024-09-01
Avanço Físico | 100% | 100% | 73% | 12% | - | -
Antecipação Esperada | 17 ﻿months* | 16 ﻿months* | 12 ﻿months | 14 ﻿months | 12/18 ﻿months | -
Entrada em Operação | 2020-03-01 | 2020-11-01 | - | - | - | -
CAPEX Leilão (R$)** | 295294125.78 | 329790787.72 | 479795926 | 699422704.54 | 882240000 | 74914000
Rap Leilão (R$)** | 58818710 | 65776580 | 78284220 | 116061645.85 | 119712580 | 11008060
Rap Energisa (R$)** | 36702875.04 | 46320000 | 33515000 | 62854451 | 63000000 | 4094777
Deságio | 37.6% | 29.58% | 57.19% | 45.84% | 47.37% | 62.8%
Finalidade | Reinforcements to serve Mato Grosso do Sul state, increasing the reliability of the system/quality | Reinforcement to supply electricity to the region of Santana do Araguaia and increase the reliability and quality of the service for clients in the north-east region of Mato Grosso. | Expanding the National Grid to enable us to handle the increasing loads in the south-east region of Pará state which has major mining and agricultural activity | Carrying the potential hydraulic and photovoltaic generation from the states of Bahia and Tocantins, in addition to supplying the regions of Dianópolis and Gurupi in Tocantins state. | Supplying electricity to the metropolitan region of Manaus and Presidente Figueiredo, in Amazonas state. | Supplying the region of Gurupi
*Advance Completion
** Figures valid as of the respective auction dates
INDEX

## Investments
Capex Schecule | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
EGO I | 3% | 35% | 49% | 13%
EPA I | 3% | 26% | 46% | 25%
EPA II |  | 1% | 20% | 42% | 33% | 4%
ETT |  |  | 3% | 4% | 59% | 34%
EAM |  |  |  |  | 40.11% | 7.29% | 20.92% | 23.3% | 6.4% | 1.38% | 0.29% | 0.31%
Investments Performed | 2017 | 2018 | 2019 | 2020 | 2021 | Total
EGO I | 6 | 90.5 | 124.1 | 33.8 |  | 254.4
EPA I | 8.7 | 79.7 | 152 | 78 |  | 318.4
EPA II |  | 2.9 | 73.6 | 137.1 | 75.6 | 289.2
ETT |  |  | 15.9 | 33.3 | 32.2 | 81.4
EAM | [5 empty] | 0
| 14.7 | 173.1 | 365.6 | 282.2 | 107.8 | 943.4
INDEX

## Financing
Operation | Infrastructure Debenture | Fundo Constitucional de Finan.do Norte (Banco da Amazônia) | 4131 | Fundo Constitucional de Finan.do Norte (Banco da Amazônia) | Infrastructure Debenture | Debenture
Company | Energisa Transmissora | EPA I | Energisa Transmissora | EPA II | Energisa Transmissora | Energisa Transmissora
Amount (R$ M) | 250 | 201.3 | 135 | 250 | 250 | 300
Debt Cost | 104,6% of CDI | IPCA + 1.88% | CDI + 0.65% | IPCA + 1.68% | 1st series: IPCA + 4.23% 2nd series: IPCA + 4.47% | CDI + 1.8%
Maturity Date | 1st series: Dec/2025 2nd series: Dec/2028 3rd series: Dec/2028 | Jul/39 | Feb/23 | 1940-07-01 | 1st series: Oct/2027 2nd series: Oct/2030 | Mar/24
INDEX