## Índice.Index
Português | English
Resumo
Investimentos
Financiamento
Summary
Investments
Financing

## Resumo
Resumo | EGO I | EPA I | EPA II | ETT | EAM | ETT II | EAP | EAM II | EMA | Energisa Paranaíta | LMTE | LXTE | LTTE
Data do Leilão | 2017-04-24 | 2017-04-24 | 2018-06-28 | 2018-12-20 | 2020-12-17 | 2021-06-30 | 2021-12-17 | 2022-06-30 | 2024-03-28 | - | - | - | -
UF | GO | PA | PA | TO / BA | AM | TO | AP | EAM | MA/PI | MT | PA | PA/AP | RJ/SP
Extensão (Km) | 136 | 296 | 138.8 | 772 | 408 | SE | 10 | 12.9 | 393.53 | SE | 685 | 508 | 258
Tipo de Circuito | CD | CD | CD | - | CD / CS | - | - | 1 | 1 | - | - | - | -
Potência (MVA) | 1344 | 300 | 1800 | 850 | 2050 | 200 | 300 | - | - | 150 | 1000 | 1500 | 4200
Assinatura do Contrato | 2017-08-11 | 2017-08-11 | 2018-09-21 | 2019-03-25 | 2021-03-31 | 2021-09-30 | 2022-03-26 | 2022-08-31 | 2024-06-28 | 2016-06-27 | 2008-10-16 | 2008-10-16 | 2011-12-09
Final de concessão | ago/2047 | ago/2047 | set/2048 | mar/2049 | mar/2051 | set/2051 | mar/2052 | ago/2052 | 2054-06-01 | jun/2046 | out/2038 | out/2038 | dez/2041
Emissão da Licença de Instalação | 2018-09-13 | 2018-10-02 | 2019-05-06 | 19/10/2020 (2 linhas) | - | - | - | - | - | - | - | - | -
Prazo Aneel | 2021-08-01 | 2022-02-01 | 2023-03-01 | 2024-03-01 | 2026-03-01 | 2024-09-01 | 2025-09-01 | 2027-08-01 | 2023-06-01 | - | - | - | -
Avanço Físico | 100% | 100% | 100% | 20% | 30.04% | - | - | - | - | - | - | - | -
Antecipação Esperada | 17 meses(a) | 16 meses(a) | 15 meses(a) | 14 meses | 12/18 meses | - | 8 meses | 18 meses | - | - | - | - | -
Entrada em Operação | 2020-03-01 | 2020-11-01 | Fase 1: fev/21 - Fase 2 e 3: Dez/21 | Fase 1: nov/22 - Fase 2: Dez/22 | - | - | - | - | - | jun/2019 | jun/2013 | jun/2013 | jun/2018
Data de Aquisição | - | - | - | - | - | - | - | - | - | fev/2022 | jun/2022 | jun/2022 | jun/2022
CAPEX Leilão (R$)(b) | 295294125.78 | 329790787.72 | 479795926 | 699422704.54 | 882240000 | 74914000 | 161675036 | 209785188 | 935501893.8276 | - | - | - | -
Capex Atualizado/Preço de aquisição (R$) | 255911700.61 | 318256880.78 | 421155183.73 | 756223809.6 | 791399511 | 86537568.726 | 185047691 | 227623616 | 936900961 | 102086114.96 | 802714914.38
RAP Leilão (R$)(b) | 58818710 | 65776580 | 78284220 | 116061645.85 | 119712580 | 11008060 | 22018023.41 | 17684000 | - | - | - | - | -
RAP Energisa (R$)(b) | 36702875.04 | 46320000 | 33515000 | 62854451 | 63000000 | 4094777 | 11300000 | 32306394.47 | 125000000 | - | - | - | -
RAP ciclo 2024/2025 | 52.143.366,50 | 65.237.673,02 | 53.222.424,22 | 85.450.273,39 | 86.343.019,32 | 5.169.826,52 | 13.637.743,71 | 20.161.720,00 | 125000000 | 13.165.544,60 | 186.462.775,59 (c) | 197893418,17(c) | 81.426.041,60(c)
Deságio | 37.6% | 29.58% | 57.19% | 45.84% | 47.37% | 62.8% | 48.68% | 45.26% | 29.99% | - | - | - | -
Regime fiscal | Lucro Presumido | Lucro Presumido | Lucro Presumido | Lucro Real | Lucro Presumido | Lucro Presumido | Lucro Presumido | Lucro Presumido | Lucro Real | Lucro Presumido | Lucro Real | Lucro Real | Lucro Real
Benefício Fiscal | - | - | - | SUDAM | SUDAM (a partir do momento que começar a utilizar o regime de lucro real) | - | - | - | - | - | SUDAM | SUDAM | -
Finalidade | Reforços para atendimento ao estado do Mato Grosso do Sul com aumento da confiabilidade do sistema/qualidade | Reforço para o suprimento à região de Santana do Araguaia e aumento na qualidade e confiabilidade do atendimento aos clientes da região nordeste de Mato Grosso. | Expansão da rede básica para possibilitar o atendimento ao crescimento das cargas da região sudeste do Pará que possui grande atividade minerária e agropecuária | Escoamento do potencial de geração hidráulica e fotovoltaico nos estados da Bahia e do Tocantins, além de suprimento para a região de Dianópolis e Gurupi no estado do Tocantins | Atendimento elétrico à região metropolitana de Manaus e Presidente Figueiredo, no estado do Amazonas. | Suprimento à região de Gurupi | Aumento da confiabilidade do sistema de transmissão para atendimento ao estado do Amapá | Proverá atendimento à região metropolitana de Manaus | - | Faz conexão com a Energisa Mato Grosso Distribuidora de Energia | - | - | -
(a)Antecipação Real
(b) Números com data base dos respectivos leilões
(c) LMTE Considera receitas adicionais de R$ 22,2 milhões referentes aos contratos de fibra ótica e R$ 2,2 milhões referente à REA nº 11.996/22; LXTE Considera RAP adicional de R$ 8,6 milhões referente à REA nº 5.149/15 e receita adicional de R$ 16,7 milhões referente aos contratos de fibra ótica; e LTTE Considera receitas adicionais de R$ 21,3 milhões referente às REA nº 6.079/16 e nº 8.647/20
ÍNDICE
Note on F16: Capex não considera a indenização de R$ 256 milhões referentes aos ativos operacionais transferidos à EAM.
Note on F19: A Companhia já recebe 30,04% da RAP referente as instalações operacionais da EAM

## Investimentos
Cronograma de Desembolso | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029
EGO I | 3% | 35% | 49% | 13%
EPA I | 3% | 26% | 46% | 25%
EPA II |  | 1% | 20% | 42% | 33% | 4%
ETT |  |  | 2.21% | 4.65% | 52.52% | 35.95% | 4.67%
EAM |  |  |  |  | 28.68% | 8.35% | 22.09% | 25.96% | 7.37% | 5.02% | 1.09% | 2%
ETT II |  |  |  |  | 2.84% | 7.76% | 57% | 33%
EAP | [5 empty] | 5.24% | 31% | 62% | 2%
EAM II | [5 empty] | 8% | 48% | 27% | 17%
EMA | [7 empty] | 2% | 5% | 7% | 40% | 22% | 24%
Investimentos já realizados | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 1T23 | 2T23 | 3T23 | 4T23 | 1T24 | 2T24 | 3T24 | Total
EGO I | 6 | 90.5 | 124.1 | 33.8 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254.4
EPA I | 8.7 | 79.7 | 152 | 78 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318.4
EPA II |  | 2.9 | 73.6 | 137.1 | 187.1 | 52.565 | 10.441 | 9.726 | 0 | 0 | 0 | 0 | 0 | 473.432
ETT |  |  | 15.9 | 33.3 | 376.6 | 414.716 | 46.587 | 31.303 | 106.45 | 0 | 0 | 0 | 0 | 1024.856
EAM |  |  |  |  | 257.3 | 84.707 | 37.434 | 63.307 | 47.521 | 74.74 | 41.5 | 72.4 | 58.9 | 737.809
ETT II |  |  |  |  | 2.005 | 5.439 | 3.014 | 14.492 | 12.473 | 9.94 | 4 | 2 | 16.4 | 69.763
EAP |  |  |  |  | 0 | 8.147 | 3.254 | 13.886 | 3.939 | 26.74 | 31.4 | 32.3 | 15 | 134.666
EAM II | [5 empty] | 0 | 0 | 0 | 7.898 | 11.2 | 0.8 | 13.4 | 28.7 | 61.998
Gemini | [5 empty] | 0.686 | 0.146 | 4.233 | 6.502 | 19.7 | 10.5 | 8 | 35.3 | 85.067
| 14.7 | 173.1 | 365.6 | 282.2 | 823.005 | 566.26 | 100.876 | 136.947 | 184.783 | 142.32 | 88.2 | 128.1 | 154.3 | 3160.391
ÍNDICE

## Financiamento
Operação Contratada | Debênture de Infra | Fundo Constitucional de Finan.do Norte (Banco da Amazônia) | 4131 | Fundo Constitucional de Finan.do Norte (Banco da Amazônia) | Debênture de Infra | Debênture | Debêntures Privada de Infra | Nota Comercial | Debênture
Empresa | Energisa Transmissora | EPA I | Energisa Transmissora | EPA II | Energisa Transmissora | Energisa Transmissora | Energisa Amazonas Transmissora de Energia | Energisa Transmissora | Energisa Transmissora
Montante (R$ mm) | 250 | 201.3 | 135 | 250 | 140 | 300 | 41.6 | 350 | 500
Custo da dívida | 104,6% do CDI | IPCA + 1,88% | CDI + 0,65% | IPCA + 1,68% | 1a série: IPCA + 4,23% 2a série: IPCA + 4,47% | CDI + 1,8% | IPCA + 6,087% | CDI + 1,45% | CDI + 1,25%
Prazo | 1ª série: dez/2025 2ª série: dez/2028 3ª série: dez/2025 | 1939-07-01 | 2023-02-01 | 1940-07-01 | 1a série: out/2027 2a série: out/2030 | 2024-03-01 | 1ª série: out/2031 | 2025-06-01 | 2023-07-01
ÍNDICE

## Summary
Summary | EGO I | EPA I | EPA II | ETT | EAM | ETT II | EAM II | EAP | EAM | Paranaíta | LMTE | LXTE | LTTE
Auction Date | 04/24/2017 | 04/24/2017 | 06/28/2018 | 12/20/2018 | 12/17/2020 | 06/30/2021 | 06/30/2022 | = | 03/28/2024 | - | - | - | -
Location | GO | PA | PA | TO / BA | AM | TO | AM | AP | MA/PI | MT | PA | PA/AP | RJ/SP
Extension (Km) | 136 | 296 | 138.8 | 772 | 410 | - | 12.9 | 10 | 393.53 | SE | 685 | 508 | 258
Circuit Type | DC | DC | DC | - | DC / CS | - | 1 | - | 1 | - | - | - | -
Power (MVA) | 1344 | 300 | 1800 | 850 | 2050 | 200 | - | 300 | - | 150 | 1000 | 1500 | 4200
Contract Signature | 2017-11-08 | 2017-11-08 | 09/21/2018 | 03/25/2019 | 03/31/2021 | 09/30/2021 | 08/31/2022 | Expectation: mar/2022 | 06/28/2024 | 06/27/2016 | 2008-10-16 | 2008-10-16 | 2011-12-09
End of concession | aug/2047 | aug/2047 | sep/2048 | mar/2049 | mar/2051 | sep/2051 | mar/2052 | aug/2052 | 2054-06-01 | jun/2046 | oct/2038 | oct/2038 | dec/2041
Issuance of the Installation License | 09/13/2018 | 2018-02-10 | 2019-06-05 | 19/10/2020 (2 lines) | - | - | - | - | - | - | - | - | -
Aneel deadline | aug/2021 | feb/2022 | 2023-03-01 | 2024-03-01 | 2026-03-01 | sep/2024 | aug/2027 | sep/2025 | 2023-06-01 | - | - | - | -
Progress | 100% | 100% | 100% | 20% | 30.04% | - | - | - | - | - | - | - | -
Anticipation | 17 ﻿months (a) | 16 ﻿months (a) | 15 ﻿months (a) | 14 ﻿months | 12/18 ﻿months | - | 18 months | 8 ﻿months | - | - | - | - | -
Entry into Operation | 2020-03-01 | 2020-11-01 | Phase 1: feb/21 - Phase 2 and 3: Dec/21 | Phase 1: nov/22 - Phase 2: Dec/22 | - | - | - | - | - | 06/27/2019 | jun/2013 | jun/2013 | jun/2018
Acquisition date | - | - | - | - | - | - | - | - | - | feb/2022 | - | - | -
CAPEX Auction (R$) (b) | 295294125.78 | 329790787.72 | 479795926 | 699422704.54 | 882240000 | 74914000 | 209785188 | 161675036 | 935501893.8276 | 100688937.37 | - | - | -
Updated Capex (R$) | 255911700.61 | 318256880.78 | 421155183.73 | 756223809.6 | 791399511 | 86537568.726 | 185047691 | 227623616 | 936900961 | 102086114.96 | 802714914.38
Rap Auction (R$)(b) | 58818710 | 65776580 | 78284220 | 116061645.85 | 119712580 | 11008060 | 17684000 | 22018023.41 | - | - | - | - | -
Rap Energisa (R$)(b) | 36702875.04 | 46320000 | 33515000 | 62854451 | 63000000 | 4094777 | 32306394.47 | 11300000 | 125000000 | - | - | - | -
2023/2024 Rap Cycle | 51604976.41 | 65126845.87 | 50228237.37 | 83050021.9 | 83081235.96 | 4974525.79 | 13122550.18 | 19400069.95 | 125000000 | 12668189.33 | 177.456.641,89 (c) | 179.331.721,54 (c) | 78.350.436,55(c)
Discount | 37.6% | 29.58% | 57.19% | 45.84% | 47.37% | 62.8% | -45.26% | 48.68% | 29.99% | - | - | - | -
Tax Regime | Presumed profit | Presumed profit | Presumed profit | Real profit | Presumed profit | Presumed profit | Presumed profit | Presumed profit | Real profit | Presumed profit | Real Profit | Real Profit | Real Profit
Fiscal Benefit | - | - | - | SUDAM | SUDAM (from the moment you start using the real profit regime) | - | - | - | - | - | SUDAM | SUDAM | -
Goal | Reinforcements to serve Mato Grosso do Sul state, increasing the reliability of the system/quality | Reinforcement to supply electricity to the region of Santana do Araguaia and increase the reliability and quality of the service for clients in the north-east region of Mato Grosso. | Expanding the National Grid to enable us to handle the increasing loads in the south-east region of Pará state which has major mining and agricultural activity | Carrying the potential hydraulic and photovoltaic generation from the states of Bahia and Tocantins, in addition to supplying the regions of Dianópolis and Gurupi in Tocantins state. | Supplying electricity to the metropolitan region of Manaus and Presidente Figueiredo, in Amazonas state. | Supplying the region of Gurupi | Provide service to the metropolitan region of Manaus | Increase in the reliability of the transmission system to serve the state of Amapá | - | It connects with Energisa Mato Grosso Distribuidora de Energia | - | - | -
(a) Advance Completion
(b) Figures valid as of the respective auction dates
(c) LMTE Considers additional revenues of R$ 22.2 million related to fiber optic contracts and additional RAP of R$ 2.2 million referring to REA No. 11,996/22; LXTE considers additional RAP of R$ 8.6 million referring to REA No. 5,149/15 and additional revenue of R$ 16.7 million referring to fiber optic contracts; and LTTE considers additional revenues of R$ 21.3 million referring to REA No. 6,079/16 and No. 8,647/20
INDEX
Note on F16: Capex does not consider the indemnity of R$ 256 million referring to the operational assets transferred to EAM
Note on F19: The Company already receives 30.04% of the RAP referring to EAM's operating facilities

## Investments
Capex Schecule | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029
EGO I | 3% | 35% | 49% | 13%
EPA I | 3% | 26% | 46% | 25%
EPA II |  | 1% | 20% | 42% | 33% | 4%
ETT |  |  | 2.21% | 4.65% | 52.52% | 35.95% | 4.67%
EAM |  |  |  |  | 28.68% | 8.35% | 22.09% | 25.96% | 7.37% | 5.02% | 1.09% | 2%
ETT II |  |  |  |  | 2.84% | 7.76% | 57% | 33%
EAP | [5 empty] | 5.24% | 31% | 62% | 2%
EAM II | [5 empty] | 8% | 48% | 27% | 17%
EMA | [7 empty] | 2% | 5% | 7% | 40% | 22% | 24%
Investments Performed | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 1Q23 | 2Q23 | 3Q23 | 4Q23 | 1Q24 | 2Q24 | 3Q24 | Total
EGO I | 6 | 90.5 | 124.1 | 33.8 | - |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 254.4
EPA I | 8.7 | 79.7 | 152 | 78 | - |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 318.4
EPA II |  | 2.9 | 73.6 | 137.1 | 187.1 | 52.565 | 10.441 | 9.726 | 0 | 0 | 0 | 0 | 0 | 473.432
ETT |  |  | 15.9 | 33.3 | 376.6 | 414.716 | 46.587 | 31.303 | 106.45 | 0 | 0 | 0 | 0 | 1024.856
EAM |  |  |  |  | 257.3 | 84.707 | 37.434 | 63.307 | 47.521 | 74.74 | 41.5 | 72.4 | 58.9 | 737.809
ETT II |  |  |  |  | 2.005 | 5.439 | 3.014 | 14.492 | 12.473 | 9.94 | 4 | 2 | 16.4 | 69.763
EAP | [5 empty] | 8.147 | 3.254 | 13.886 | 3.939 | 26.74 | 31.4 | 32.3 | 15 | 134.666
EAM II | [7 empty] | 0 | 7.898 | 11.2 | 0.8 | 13.4 | 28.7 | 61.998
Gemini | [5 empty] | 0.686 | 0.146 | 4.233 | 6.502 | 19.7 | 10.5 | 8 | 35.3 | 85.067
| 14.7 | 173.1 | 365.6 | 282.2 | 823.005 | 566.26 | 100.876 | 136.947 | 184.783 | 142.32 | 88.2 | 128.1 | 154.3 | 3160.391
INDEX

## Financing
Operation | Infrastructure Debenture | Constitutional Fund for Financing of the North (Banco da Amazônia) | 4131 | Constitutional Fund for Financing of the North (Banco da Amazônia) | Infrastructure Debenture | Debenture | Private Infrastructure Debenture | Commercial Note | Debenture
Company | Energisa Transmissora | EPA I | Energisa Transmissora | EPA II | Energisa Transmissora | Energisa Transmissora | Energisa Amazonas Transmissora de Energia | Energisa Transmissora | Energisa Transmissora
Amount (R$ M) | 250 | 201.3 | 135 | 250 | 140 | 300 | 41.6 | 350 | 500
Debt Cost | 104,6% of CDI | IPCA + 1.88% | CDI + 0.65% | IPCA + 1.68% | 1st series: IPCA + 4.23% 2nd series: IPCA + 4.47% | CDI + 1.8% | IPCA + 6.087% | CDI + 1.45% | CDI + 1.25%
Maturity Date | 1st series: Dec/2025 2nd series: Dec/2028 3rd series: Dec/2028 | Jul/39 | Feb/23 | 1940-07-01 | 1st series: Oct/2027 2nd series: Oct/2030 | Mar/24 | 1st series: oct/2031 | 2025-06-01 | 2023-07-01
INDEX