## Índice.Index
Português | English
Resumo
Investimentos
Financiamento
Summary
Investments
Financing

## Resumo
Resumo | EGO I | EPA I | EPA II | ETT | EAM | ETT II | EAP | EAM II | Energisa Paranaíta | LMTE | LXTE | LTTE
Data do Leilão | 2017-04-24 | 2017-04-24 | 2018-06-28 | 2018-12-20 | 2020-12-17 | 2021-06-30 | 2021-12-17 | 2022-06-30 | - | - | - | -
UF | GO | PA | PA | TO / BA | AM | TO | AP | EAM | MT | PA | PA/AP | RJ/SP
Extensão (Km) | 136 | 296 | 138.8 | 772 | 408 | SE | 10 | 12.9 | SE | 685 | 508 | 258
Tipo de Circuito | CD | CD | CD | - | CD / CS | - | - | 1 | - | - | - | -
Potência (MVA) | 1344 | 300 | 1800 | 850 | 2050 | 200 | 300 | - | 150 | 1000 | 1500 | 4200
Assinatura do Contrato | 2017-08-11 | 2017-08-11 | 2018-09-21 | 2019-03-25 | 2021-03-31 | 2021-09-30 | 2022-03-26 | 2022-08-31 | 2016-06-27 | 2008-10-16 | 2008-10-16 | 2011-12-09
Final de concessão | ago/2047 | ago/2047 | set/2048 | mar/2049 | mar/2051 | set/2051 | mar/2052 | ago/2052 | jun/2046 | out/2038 | out/2038 | dez/2041
Emissão da Licença de Instalação | 2018-09-13 | 2018-10-02 | 2019-05-06 | 19/10/2020 (2 linhas) | - | - | - | - | - | - | - | -
Prazo Aneel | 2021-08-01 | 2022-02-01 | 2023-03-01 | 2024-03-01 | 2026-03-01 | 2024-09-01 | 2025-09-01 | 2027-08-01 | - | - | - | -
Avanço Físico | 100% | 100% | 100% | 20% | 30.04% | - | - | - | - | - | - | -
Antecipação Esperada | 17 meses(a) | 16 meses(a) | 15 meses(a) | 14 meses | 12/18 meses | - | 8 meses | 18 meses | - | - | - | -
Entrada em Operação | 2020-03-01 | 2020-11-01 | Fase 1: fev/21 - Fase 2 e 3: Dez/21 | - | - | - | - | - | jun/2019 | jun/2013 | jun/2013 | out/2017
Data de Aquisição | - | - | - | - | - | - | - | - | fev/2022 | jun/2022 | jun/2022 | jun/2022
CAPEX Leilão (R$)(b) | 295294125.78 | 329790787.72 | 479795926 | 699422704.54 | 882240000 | 74914000 | 161675036 | 209785188 | - | - | - | -
Capex Atualizado/Preço de aquisição (R$) | 254400000 | 318400000 | 424029848.1279 | 742725159.9954 | 1011016902.7801 | 82733492.9165 | 147580188.3072 | 207068775.3365 | 102086114.96 | 802714914.38
RAP Leilão (R$)(b) | 58818710 | 65776580 | 78284220 | 116061645.85 | 119712580 | 11008060 | 22018023.41 | 17684000 | - | - | - | -
RAP Energisa (R$)(b) | 36702875.04 | 46320000 | 33515000 | 62854451 | 63000000 | 4094777 | 11300000 | 32306394.47 | - | - | - | -
RAP ciclo 2022/2023 | 49650805.6 | 62660630.67 | 48326200.71 | 79905094.03 | 79935126.01 | 4786151.09 | 12625627.07 | 18665407.18 | 12188471.94 | 164.488.186,73 (c) | 173.010.667,96 (c) | 75.225.218,83(c)
Deságio | 37.6% | 29.58% | 57.19% | 45.84% | 47.37% | 62.8% | 48.68% | -45.26% | - | - | - | -
Regime fiscal | Lucro Presumido | Lucro Presumido | Lucro Presumido | Lucro Presumido | Lucro Presumido | Lucro Presumido | Lucro Presumido | Lucro Presumido | Lucro Presumido | Lucro Real | Lucro Real | Lucro Real
Benefício Fiscal | - | - | - | SUDAM (a partir do momento que começar a utilizar o regime de lucro real) | SUDAM (a partir do momento que começar a utilizar o regime de lucro real) | - | - | - | - | SUDAM | SUDAM | -
Finalidade | Reforços para atendimento ao estado do Mato Grosso do Sul com aumento da confiabilidade do sistema/qualidade | Reforço para o suprimento à região de Santana do Araguaia e aumento na qualidade e confiabilidade do atendimento aos clientes da região nordeste de Mato Grosso. | Expansão da rede básica para possibilitar o atendimento ao crescimento das cargas da região sudeste do Pará que possui grande atividade minerária e agropecuária | Escoamento do potencial de geração hidráulica e fotovoltaico nos estados da Bahia e do Tocantins, além de suprimento para a região de Dianópolis e Gurupi no estado do Tocantins | Atendimento elétrico à região metropolitana de Manaus e Presidente Figueiredo, no estado do Amazonas. | Suprimento à região de Gurupi | Aumento da confiabilidade do sistema de transmissão para atendimento ao estado do Amapá | Proverá atendimento à região metropolitana de Manaus | Faz conexão com a Energisa Mato Grosso Distribuidora de Energia | - | - | -
(a)Antecipação Real
(b) Números com data base dos respectivos leilões
(c) LMTE Considera receitas adicionais de R$ 22,2 milhões referentes aos contratos de fibra ótica e R$ 2,2 milhões referente à REA nº 11.996/22; LXTE Considera RAP adicional de R$ 8,6 milhões referente à REA nº 5.149/15 e receita adicional de R$ 16,7 milhões referente aos contratos de fibra ótica; e LTTE Considera receitas adicionais de R$ 21,3 milhões referente às REA nº 6.079/16 e nº 8.647/20
ÍNDICE

## Investimentos
Cronograma de Desembolso | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
EGO I | 3% | 35% | 49% | 13%
EPA I | 3% | 26% | 46% | 25%
EPA II |  | 1% | 20% | 42% | 33% | 4%
ETT |  |  | 2.33% | 4.71% | 54.58% | 38.38%
EAM |  |  |  |  | 35.71% | 7.15% | 21.87% | 25.61% | 7.29% | 1.63% | 0.35% | 0.39%
ETT II |  |  |  |  | 4.01% | 6.35% | 27.16% | 62.48%
EAP | [5 empty] | 10.04% | 14.28% | 61.84% | 13.83%
EAM | [5 empty] | 2.16% | 9.93% | 47.86% | 26.78% | 13.27%
Investimentos já realizados | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
EGO I | 6 | 90.5 | 124.1 | 33.8 | - | 0 | 254.4
EPA I | 8.7 | 79.7 | 152 | 78 | - | 0 | 318.4
EPA II |  | 2.9 | 73.6 | 137.1 | 187.1 | 52.565 | 453.265
ETT |  |  | 15.9 | 33.3 | 376.6 | 414.716 | 840.516
EAM |  |  |  |  | 257.3 | 84.707 | 342.007
ETT II |  |  |  |  | 2.005 | 5.439 | 7.444
EAP |  |  |  |  | 0 | 8.147 | 8.147
EAM | [5 empty] | 0 | 0
Gemini | [5 empty] | 0.686 | 0.686
| 14.7 | 173.1 | 365.6 | 282.2 | 823.005 | 566.26 | 2224.865
ÍNDICE

## Financiamento
Operação Contratada | Debênture de Infra | Fundo Constitucional de Finan.do Norte (Banco da Amazônia) | 4131 | Fundo Constitucional de Finan.do Norte (Banco da Amazônia) | Debênture de Infra | Debênture | Debêntures Privada de Infra
Empresa | Energisa Transmissora | EPA I | Energisa Transmissora | EPA II | Energisa Transmissora | Energisa Transmissora | Energisa Amazonas Transmissora de Energia
Montante (R$ mm) | 250 | 201.3 | 135 | 250 | 250 | 300 | 41.6
Custo da dívida | 104,6% do CDI | IPCA + 1,88% | CDI + 0,65% | IPCA + 1,68% | 1a série: IPCA + 4,23% 2a série: IPCA + 4,47% | CDI + 1,8% | IPCA + 6,087%
Prazo | 1ª série: dez/2025 2ª série: dez/2028 3ª série: dez/2025 | 1939-07-01 | 2023-02-01 | 1940-07-01 | 1a série: out/2027 2a série: out/2030 | 2024-03-01 | 1ª série: out/2031
ÍNDICE

## Summary
Summary | EGO I | EPA I | EPA II | ETT | EAM | ETT II | EAM II | EAP | Paranaíta | LMTE | LXTE | LTTE
Auction Date | 04/24/2017 | 04/24/2017 | 06/28/2018 | 12/20/2018 | 12/17/2020 | 06/30/2021 | 06/30/2022 | 12/17/2021 | - | - | - | -
Location | GO | PA | PA | TO / BA | AM | TO | AM | AP | MT | PA | PA/AP | RJ/SP
Extension (Km) | 136 | 296 | 138.8 | 772 | 410 | - | 12.9 | 10 | SE | 685 | 508 | 258
Circuit Type | DC | DC | DC | - | DC / CS | - | 1 | - | - | - | - | -
Power (MVA) | 1344 | 300 | 1800 | 850 | 2050 | 200 | - | 300 | 150 | 1000 | 1500 | 4200
Contract Signature | 2017-11-08 | 2017-11-08 | 09/21/2018 | 03/25/2019 | 03/31/2021 | 09/30/2021 | 08/31/2022 | Expectation: mar/2022 | 06/27/2016 | 2008-10-16 | 2008-10-16 | 2011-12-09
End of concession | aug/2047 | aug/2047 | sep/2048 | mar/2049 | mar/2051 | sep/2051 | mar/2052 | aug/2052 | jun/2046 | oct/2038 | oct/2038 | dec/2041
Issuance of the Installation License | 09/13/2018 | 2018-02-10 | 2019-06-05 | 19/10/2020 (2 lines) | - | - | - | - | - | - | - | -
Aneel deadline | aug/2021 | feb/2022 | 2023-03-01 | 2024-03-01 | 2026-03-01 | sep/2024 | aug/2027 | sep/2025 | - | - | - | -
Progress | 100% | 100% | 100% | 20% | 30.04% | - | - | - | - | - | - | -
Anticipation | 17 ﻿months (a) | 16 ﻿months (a) | 15 ﻿months (a) | 14 ﻿months | 12/18 ﻿months | - | 18 months | 8 ﻿months | - | - | - | -
Entry into Operation | 2020-03-01 | 2020-11-01 | - | - | - | - | - | - | 06/27/2019 | jun/2013 | jun/2013 | oct/2017
Acquisition date | - | - | - | - | - | - | - | - | feb/2022 | - | - | -
CAPEX Auction (R$) (b) | 295294125.78 | 329790787.72 | 479795926 | 699422704.54 | 882240000 | 74914000 | 209785188 | 161675036 | 100688937.37 | - | - | -
Updated Capex (R$) | 254400000 | 318400000 | 424029848.1279 | 742725159.9954 | 1011016902.7801 | 82733492.9165 | 147580188.3072 | 207068775.3365 | 102086114.96 | 802714914.38
Rap Auction (R$)(b) | 58818710 | 65776580 | 78284220 | 116061645.85 | 119712580 | 11008060 | 17684000 | 22018023.41 | - | - | - | -
Rap Energisa (R$)(b) | 36702875.04 | 46320000 | 33515000 | 62854451 | 63000000 | 4094777 | 32306394.47 | 11300000 | - | - | - | -
2022/2023 Rap Cycle | 49650805.6 | 62660630.67 | 48326200.71 | 79905094.03 | 79935126.01 | 4786151.09 | 12625627.07 | 18665407.18 | 12188471.94 | 164.488.186,73 (c) | 173.010.667,96 (c) | 75.225.218,83 (c)
Discount | 37.6% | 29.58% | 57.19% | 45.84% | 47.37% | 62.8% | -45.26% | 48.68% | - | - | - | -
Tax Regime | Presumed profit | Presumed profit | Presumed profit | Presumed profit | Presumed profit | Presumed profit | Presumed profit | Presumed profit | Presumed profit | Real Profit | Real Profit | Real Profit
Fiscal Benefit | - | - | - | SUDAM (from the moment you start using the real profit regime) | SUDAM (from the moment you start using the real profit regime) | - | - | - | - | SUDAM | SUDAM | -
Goal | Reinforcements to serve Mato Grosso do Sul state, increasing the reliability of the system/quality | Reinforcement to supply electricity to the region of Santana do Araguaia and increase the reliability and quality of the service for clients in the north-east region of Mato Grosso. | Expanding the National Grid to enable us to handle the increasing loads in the south-east region of Pará state which has major mining and agricultural activity | Carrying the potential hydraulic and photovoltaic generation from the states of Bahia and Tocantins, in addition to supplying the regions of Dianópolis and Gurupi in Tocantins state. | Supplying electricity to the metropolitan region of Manaus and Presidente Figueiredo, in Amazonas state. | Supplying the region of Gurupi | Provide service to the metropolitan region of Manaus | Increase in the reliability of the transmission system to serve the state of Amapá | It connects with Energisa Mato Grosso Distribuidora de Energia | - | - | -
(a) Advance Completion
(b) Figures valid as of the respective auction dates
(c) LMTE Considers additional revenues of R$ 22.2 million related to fiber optic contracts and additional RAP of R$ 2.2 million referring to REA No. 11,996/22; LXTE considers additional RAP of R$ 8.6 million referring to REA No. 5,149/15 and additional revenue of R$ 16.7 million referring to fiber optic contracts; and LTTE considers additional revenues of R$ 21.3 million referring to REA No. 6,079/16 and No. 8,647/20
INDEX

## Investments
Capex Schecule | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
EGO I | 3% | 35% | 49% | 13%
EPA I | 3% | 26% | 46% | 25%
EPA II |  | 1% | 20% | 42% | 33% | 4%
ETT |  |  | 2.33% | 4.71% | 54.58% | 38.38%
EAM |  |  |  |  | 35.71% | 7.15% | 21.87% | 25.61% | 7.29% | 1.63% | 0.35% | 0.39%
ETT II |  |  |  |  | 4.01% | 6.35% | 27.16% | 62.48%
EAP | [5 empty] | 10.04% | 14.28% | 61.84% | 13.83%
EAM | [5 empty] | 1.887% | 8.962% | 14.62% | 59.43% | 15.09%
Investments Performed | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
EGO I | 6 | 90.5 | 124.1 | 33.8 | - |  | 254.4
EPA I | 8.7 | 79.7 | 152 | 78 | - |  | 318.4
EPA II |  | 2.9 | 73.6 | 137.1 | 187.1 | 52.565 | 453.265
ETT |  |  | 15.9 | 33.3 | 376.6 | 414.716 | 840.516
EAM |  |  |  |  | 257.3 | 84.707 | 342.007
ETT II |  |  |  |  | 2.005 | 5.439 | 7.444
EAP | [5 empty] | 8.147 | 8.147
EAM | [6 empty] | 0
Gemini | [5 empty] | 0.686 | 0.686
| 14.7 | 173.1 | 365.6 | 282.2 | 823.005 | 566.26 | 2224.865
INDEX

## Financing
Operation | Infrastructure Debenture | Constitutional Fund for Financing of the North (Banco da Amazônia) | 4131 | Constitutional Fund for Financing of the North (Banco da Amazônia) | Infrastructure Debenture | Debenture | Private Infrastructure Debenture
Company | Energisa Transmissora | EPA I | Energisa Transmissora | EPA II | Energisa Transmissora | Energisa Transmissora | Energisa Amazonas Transmissora de Energia
Amount (R$ M) | 250 | 201.3 | 135 | 250 | 250 | 300 | 41.6
Debt Cost | 104,6% of CDI | IPCA + 1.88% | CDI + 0.65% | IPCA + 1.68% | 1st series: IPCA + 4.23% 2nd series: IPCA + 4.47% | CDI + 1.8% | IPCA + 6.087%
Maturity Date | 1st series: Dec/2025 2nd series: Dec/2028 3rd series: Dec/2028 | Jul/39 | Feb/23 | 1940-07-01 | 1st series: Oct/2027 2nd series: Oct/2030 | Mar/24 | 1st series: oct/2031
INDEX